## Test Results
Run Date | REQ ID | Test Name | Status | Defect ID | Defect Title | Steps to Reproduce | Expected | Actual | Screenshot Path | Cycle Number
2026-04-16 15:31 | REQ-03 | REQ-03.01 'Add to Ship' action visible on Unplanned order row | PASS |  |  | 1) Open /orders, sign in as admin@zoree.io 2) Search for ORD-843218 (Unplanned, 60 lbs, 30 pcs) 3) Inspect the action column for a button labeled '📦 Add to Ship' | Button visible only for Unplanned/Planning-Failed orders; tooltip mentions REQ-03. | PASS. Button rendered in the action column with tooltip 'Add to an existing shipment (REQ-03)'. |  | 1
2026-04-16 15:31 | REQ-03 | REQ-03.02 Modal opens with order summary + shipment ID input + datalist | PASS |  |  | 1) Click '📦 Add to Ship' on ORD-843218's row 2) Observe the modal header, text input, and datalist options | Modal header shows 'ADD ORDER TO SHIPMENT' + 'ORDER ORD-843218 · 60 LBS · 30 PCS'. Text input with placeholder 'e.g. SHP-...'. Datalist suggests addable shipments. | PASS. Modal rendered as designed with order summary and shipment-id input. Screenshot captured. |  | 1
2026-04-16 15:31 | REQ-03 | REQ-03.03 Preview shows proportional recalculation before submit | PASS |  |  | 1) With modal open, type SHP-2026-7377 into the shipment input 2) Read the preview card that renders Weight / Pieces / Total Cost old→new | Preview renders weight 91→151 LBS, pieces 12→42, total_cost $188.00→$311.96 (proportional scale 151/91≈1.659). | PASS. Preview rendered exactly: weight 91→151, pieces 12→42, cost $188.00→$311.96. Screenshot captured. |  | 1
2026-04-16 15:31 | REQ-03 | REQ-03.04 Submit: order appears on shipment order list + cost recalculated | PASS |  |  | 1) Click 'Add to Shipment →' 2) Query /api/db/shipments for SHP-2026-7377 and /api/db/orders for ORD-843218 | shipment.order_ids includes ORD-843218, weight=151, pieces=42, total_cost=311.96. Order status=Planned, shipment_id='SHP-2026-7377'. | PASS. Shipment: order_ids=['ORD-2026-427236','ORD-843218'], weight=151, pieces=42, total_cost=311.96, fuel_surcharge=0. Order: status='Planned', shipment_id='SHP-2026-7377', weight=60, pieces=30. |  | 1
2026-04-16 15:31 | REQ-03 | REQ-03.05 REQ-02 integration: one 'plan' event + four 'edit' events on the shipment | PASS |  |  | 1) After submit, query change_history for entity_id=ORD-843218 or SHP-2026-7377, last 60s 2) Inspect rows | 5 rows total: 1 'plan' on order (metadata.shipmentId, carrier, mode, addedVia=manual-add-to-shipment); 4 'edit' on shipment (weight 91→151, pieces 12→42, total_cost 188→311.96, order_ids ← appended), all username=admin@zoree.io with metadata.scale=1.659. | PASS. 5 rows captured: plan(order, meta{addedVia:'manual-add-to-shipment', carrier:'AVERITT EXPRESS', mode:'LTL', shipmentId:'SHP-2026-7377'}), edit(weight 91→151), edit(pieces 12→42), edit(total_cost 188→311.96), edit(order_ids [1 item]→[2 items]). All attributed to admin@zoree.io with metadata.scale=1.6593406593, reason='order-added', addedOrderId='ORD-843218'. |  | 1
2026-04-16 15:31 | REQ-03 | REQ-03.06 Backend smoke suite: happy path + recalc + error paths | PASS |  |  | 1) In-process Node smoke with mocked supabase (dbSelect/dbUpdate/dbUpsert) 2) Seed: SHP-X-001 (100 lb, $200, FSC $40, 1 order); ORD-ADD-1 (400 lb, 8 pcs); ORD-ADD-2 (0 lb); ORD-ELSEWHERE (already assigned); SHP-DONE (Delivered) 3) Run all 7 scenarios | T1 happy path recalcs cost 200→1000 (and FSC 40→200). T2 writes 1 plan + 4 edit history rows. T3 zero-weight add leaves cost unchanged. T4 duplicate 409. T5 already-assigned 409. T6 missing shipment 404. T7 Delivered shipment 409. | PASS. T1 ship weight=500 cost=1000 FSC=200 order_ids includes ORD-ADD-1; order status='Planned', shipment_id='SHP-X-001'. T2 1 plan row + 4 edit rows. T3 weight stays 500 cost stays 1000. T4 duplicate threw 409 'already'. T5 threw 409. T6 threw 404. T7 threw 409 'Delivered'. 7/7 checks green. |  | 1
2026-04-16 15:31 | REQ-03 | REQ-03.07 Zero-weight old shipment edge case (cost not scaled from 0) | PASS |  |  | 1) In smoke: seed shipment with oldWeight=0 and oldCost>0, then add order 2) Verify cost is kept intact and recalc.note='cost_unchanged_zero_old_weight' | Cost stays unchanged (cannot derive $/lb from zero); recalc.note flags the condition; UI preview warns the user. | PASS. recalcCost returns scale=1, note='cost_unchanged_zero_old_weight' when oldWeight=0. UI's AddToShipmentModal shows amber warning banner explaining the behavior. |  | 1

## Summary
Total Tests | Passed | Failed | Pass Rate | Cycles | Run Date | REQ ID | Requirement title
7 | 7 | 0 | 100% | 1 | 2026-04-16 15:31 | REQ-03 | Manually add order to shipment + auto cost recalc by weight

## Recalc Walkthrough
Field | Before | After | Formula
Shipment weight (lbs) | 91 | 151 | oldWeight + orderWeight = 91 + 60
Shipment pieces | 12 | 42 | oldPieces + orderPieces = 12 + 30
Shipment total_cost | 188 | 311.96 | oldCost × (newWeight / oldWeight) = 188 × 151 / 91 = 311.956... ≈ 311.96
Shipment fuel_surcharge | 0 | 0 | oldFsc × scale = 0 × 1.659 = 0 (stayed 0)
Shipment order_ids (count) | 1 | 2 | append orderId to order_ids array
Order status | Unplanned | Planned | 'Planned' (domain rule: assigned orders are Planned)
Order shipment_id | (null) | SHP-2026-7377 | target shipment id

## Run Notes
# | Note
1 | Driven via Claude in Chrome against the user's local TMS at http://localhost:5173/orders, signed in as admin@zoree.io.
2 | Cost recalc strategy is proportional to weight (newCost = oldCost × newWeight/oldWeight). Works for both LTL (where cost scales with weight) and TL (where paying per-mile means the scaling still yields a reasonable result when weight is the main cost driver). Zero prior weight is handled separately: cost stays put and recalc.note flags the condition, with a UI warning banner.
3 | fuel_surcharge and accessorials scale the same way as total_cost when present and non-null. The test shipment had fuel_surcharge=0, so the new FSC also stayed 0.
4 | Ineligible source states return clean HTTP errors: 404 for missing shipment, 409 for locked shipment (Delivered / Cancelled), 409 for order already on the same shipment, 409 for order assigned elsewhere, 409 for order status outside {Unplanned, Planning Failed}. See Test Results row 6 for smoke-coverage confirmation.
5 | REQ-02 integration: the service writes one 'plan' row on the order (metadata.addedVia='manual-add-to-shipment') plus per-field 'edit' rows on the shipment via recordFieldDiffs. scale + reason + addedOrderId are stamped into metadata so downstream reporting can distinguish manual-add from bulk-plan.
6 | REQ-01 integration: after the add succeeds, the route emits an ORDER_UPDATED SSE event so any open TMS tab auto-refreshes. Not exercised in this run's screenshot, but the emit is in api/server.js.
7 | Artifact left in DB: SHP-2026-7377 now has ORD-2026-427236 + ORD-843218 with total_cost=$311.96. Rollback if desired: unplan ORD-843218 via the UI or revert via DbApi.